| # ID | Deliverable | Deadline |  | Metric |  | L1 deliverable |  | Current Status | Dependencies/Risks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1 | Definition of requirements for software deployment. | 31/1/2005 | Presentation/document summarising the requirements |  | Ia/Ie |  | Completed |  |  |
| D1.2 | Prototype Grid Software deployment system | 30/9/2005 | Deployment of software |  | Ia/Ie |  | Completed |  |  |
| D1.3 | Prototype semi-automatic software deployment world-wide | 31/12/2005 | Deployment and testing of software |  | Ia/Ie |  | Completed |  |  |
| D1.4 | Prototype Job Splitting and job preparation assuming dataset at a single site | 31/3/2005 | Release of prototype |  | Ib/Ie |  | Completed |  |  |
| D1.5 | Prototype Job Splitting and job preparation not assuming dataset at a single site | 30/6/2005 | Release of Prototype |  | Ib/Ie |  | Completed |  |  |
| D1.6 | Integration of CMS specific knowledge so that splitting is performed according data and resource distribution | 31/12/2005 | Release of system |  | Ib/Ie |  | Completed |  |  |
| D1.7 | Evaluation of current job monitoring tools (BOSS, Monalisa etc etc) | 30/6/2005 | Presentation/document outlining the results of the evaluation |  | Ic/Ie |  | Completed |  |  |
| D1.8 | Re-factoring of BOSS code | 31/12/2005 | Release of software |  | Ic/Ie |  | Completed |  |  |
| D1.9 | Separation of Monitoring and Logging functions | 31/12/2005 | Release of software |  | Id/Ie |  | Completed |  |  |
| D1.10 | Extension of BOSS job wrapper and the interfacing of a multiplicity of databases in BOSS | 30/6/2006 | Release of software |  | Id/Ie |  | Completed |  |  |
| D2.1 | Deployment of CMS data transfer infrastructure at RAL | 30/12/2004 |  | RAL draws data from CMS transfer infrastructure at 0.5TB per day |  | IIa |  | Completed |  |
| D2.2 | Provision of data transfer support for CMS UK physicists | 30/3/2005 |  | Datasets requested by UK physicists available at RAL |  | IIa |  | Completed |  |
| D2.3 | Contribution to effort on CMS Data Management System (DMS) | 30/6/2005 |  | Prototype DMS is described, feedback to GridPP UK Metadata group |  | IIb,IIIb |  | Completed |  |
| D2.4 | Sustained transfer of data for CMS into and out of RAL for analysis and MC production (Physics TDR) | 30/6/2005 |  | Latency between request and delivery of 1TB data of order days. |  | IIc |  | Completed |  |
| D2.5 | Codification of local practices | 30/6/2005 |  | Draft documents describing RAL local data management available |  | IIb |  | Completed |  |
| D2.6 | Rollout of CMS data transfer mechanism to UK T2s | 30/6/2005 |  | Incorporation of 2 T2 (virtual?) into CMS data distribution infrastructure. |  | IIb |  | Completed |  |
| D2.7 | Tuning of local transfer infrastructure possible | 30/9/2005 |  | Sustained data rates meet significant fraction of TDR spec |  | IId |  | Completed |  |
| D2.8 | Enhanced data management system planning | 1/1/2007 |  | Existing procedures codified and documented. New Requirements Document produced. |  | IIe |  | Completed (reported at CHEP2007, Victoria, Canada) |  |
| D2.9 | Release of Final Data Management System | 31/8/2007 |  | System ready for LHC startup and signed off by CMS. |  | IIf |  | Completed |  |
| D3.1 | RGMA verified operational on the LCG grid. | 31/10/2004 |  | Data successfully received from >5 LCG resources |  | IIIa |  | Completed (reported at IEEE NSS, Rome 2004) |  |
| D3.2 | Generation of statistically significant data from RGMA test jobs run on LCG resources | 28/2/2005 |  | At least 250000 messages transferred from LCG resources to an RGMA receiver. |  | IIIa |  | Completed (reported at IEEE NSS, Puerto Rico 2005) | LCG sites continue to deploy fully functional RGMA |
| D3.3 | Recommendations on the use of RGMA in CMS | 31/3/2005 |  | Documented analysis of the data generated in D3.2 |  | IIIa |  | Completed (Paper in IEEE/NSS Puerto Rico 2005 Conference record) |  |
| D3.4 | Metadata analysis work-plan agreed by CMS | 14/1/2005 |  | Document |  | IIIb |  | Completed | Delays in agreeing strategy for metadata management |
| D3.5 | Contribution to CMS metadata management Use Cases and initial design | 30/6/2005 |  | Contribution to metadata management section of CMS computing TDR |  | IIIb |  | Completed (see CMS TDR) | Contribution reduced if D3.4 is delayed. |
| D3.6 | Review of metadata strategies for physics data analysis in HEP experiments | 1/3/2005 |  | Document |  | IIIc |  | Completed |  |
| D3.7 | Evaluation of prototype metadata delivery system | 31/12/2005 |  | Contribution to delivered software and documentation |  | IIIc |  | RETIRED | Retired due to reallocation of Nebrensky’s effort to D4.2 |
| D3.8 | Release of production metadata delivery system | 30/6/2006 |  | Contribution to delivered software and documentation |  | IIIc |  | RETIRED | Retired due to reallocation of Nebrensky’s effort to D4.2 |
| D4.1 | Contribution to testing prototype CMS production model | 30/9/2005 |  | Production of test data sets, and numbers of data sets replicated, at the appropriate UK fraction of the CMS computing infrastructure. |  | IVa |  | Completed |  |
| D4.2 | Contribution to SC06 | 30/9/2006 |  | Production and replication of SC06 data sets at the appropriate UK fraction of the CMS computing infrastructure. |  | IVb |  | Completed |  |
| D4.3 | Contribution to restructuring of CMS data transfer infrastructure on a peer to peer architecture with examples of true autonomous agent behaviour | 30/9/2006 |  | Nodes in distribution network are self-contained, network is robust in the face of outages |  | IVc |  | Completed |  |
| D4.4 | RAL-local data management in sustained operations phase | 30/3/2007 |  | System is routinely maintained on a shift basis. High level functions operated from remote location. |  | IVc |  | Completed |  |
| D4.5 | Incorporation of all CMS sites into data transfer infrastructure | 30/6/2007 |  | All CMS T2s incorporated; minimal management required at T2s. Processes for T2 groups to routinely request and monitor data transfer in place. |  | IVc |  | Completed |  |